Six Point Action Plan for Equality

2020 – 2021

| Action | Description | Lead | Target | Completion Date |
| --- | --- | --- | --- | --- |
| Data |  |  |  |  |
| ESR | Enable and sustain self-reporting of equality data on ESR – particularly ethnicity, disability and sexual orientation | Workforce and HR | - Reduce the disability unknown percentage by 5% - down to 18% - Reduce the ethnicity unknown percentage by 3% - down to 2.08% - Reduce the sexual orientation unknown percentage by 5% - down to 23% | March 2021 |
| Equal Pay Audit | - Undertake an equal pay audit (gender), looking particularly at: - Bands 8a and above - Medical and Dental - Develop a gender balance pyramid for Executives and senior leadership | Workforce EDI | n/a | March 2021 March 2021 |
| Leavers | Continue and develop use of leavers exit interview forms | Workforce and HR | 20% of leavers completing exit interview forms | March 2021 |
| SystmOne/EMIS | - Develop Accessible Information Standard compliance project plan (to also include military veterans and carers) - Tailor and ratify Merseyside and Cheshire draft reasonable adjustments for patients policy and procedure | Chief Operating Officer (delegated as appropriate) - supported by EDI | n/a Approved policy and procedure | December 2020 March 2021 |
| Leadership & Accountability |  |  |  |  |
| NHSI Culture and Leadership Programme | Self-assessment against NHSI’s programme | Associate Director – OD |  | December 2020 |
| Board Development Plan | Develop Board EDI development plan for 2020-2021. Including race equality learning, unconscious bias and cultural competency | EDI – supported by Director for W&OD | n/a | October 2020 |
| WRES: A Model Employer | Develop and publish new stretch targets for WRES: A Model Employer based on new deadlines dates | Board – supported by EDI | TBC | October 2020 |
| Reciprocal Mentorship | Develop options for reciprocal mentorship scheme in Bridgewater for Board and senior leaders | EDI – supported by Director for W&OD | n/a | October 2020 |
| RECAP | Deliver RECAP project | EDI |  | March 2021 |
| WRES Experts | Commit to two applications for next WRES Experts programme | Board |  | TBC |
| Race At Work Charter | Roll out Charter across Trust | EDI |  | October 2020 |
| EDI training | Develop EDI training packages for: - EDI Awareness module – all staff/teams - EDI Leadership in Action Module | EDI | n/a | December 2020 December 2020 |
| Creating an inclusive culture |  |  |  |  |
| Bridgewater Anti-Bullying and Harassment (BABAH) | Refresh the BABAH campaign for 2020 – 2021 | BABAH Task and Finish Group | Improved reporting via online form and app, by 20% | March 2021 |
| Zero Tolerance | Develop and deliver zero tolerance to racism, disablism, homophobia, transphobia and religious hate project | Zero Tolerance Task and Finish Group | Improved reporting via Ulysses Improved NHS Staff Survey scores | March 2021 March 2022 |
| Race Equality Champions | Deliver training package for volunteer Race Equality Champions | EDI – supported by L&OD | Improved NHS Staff Survey scores | March 2022 |
| Disability Ambassadors | Develop a proposal for volunteer Disability Ambassadors across the Trust, based on the RCN Cultural Ambassadors programme | EDI – supported by L&OD and Director of W&OD | Improved NHS Staff Survey scores | March 2022 |
| Cultural/Diversity Celebration | - Develop first annual Cultural Diversity Celebration Week - Continue communications around annual religious and cultural celebrations and observances - Continue communications around LGBT+ and disability awareness events | Race Inclusion Network Task and Finish Group EDI EDI and Staffside | Improved NHS Staff Survey scores | March 2022 Ongoing Ongoing |
| Navajo Re-assessment | Re-assessment of Navajo Charter for LGBT+ | EDI – supported by Board and Staffside | Successful re-accreditation | December 2020 |
| Disability Confident Re-assessment | Re-assessment of Disability Confident Employer accreditation | EDI – supported by Board and staffside | Successful re-accreditation at level 2 | October 2020 |
| In My Shoes | Develop project to raise awareness of race/racism and disability/disablism to support confidence building in talking about these issues | EDI – supported by Race Inclusion Network and (Dis)Ability and Wellbeing Network | Improved NHS Staff Survey scores | March 2021 |
| FTSU | Recruit and train diverse FTSU Guardians – particularly BAME staff and staff with disabilities | FTSU Lead |  | December 2020 |
| Just and Learning Culture | Develop and deliver Just and Learning Culture programme | Task and Finish Group – supported by EDI | Improved disciplinary data, including in WRES Indicator 3 | TBC |
| Talent management and career progression |  |  |  |  |
| Recruitment | Review and refresh of recruitment policy, processes and training | Workforce and HR – supported by EDI and L&OD |  |  |
| Reciprocal Mentorship – see Leadership & Accountability |  |  |  |  |
| Positive Action | Develop positive action project plans for improving BAME and Disabled staff representation and development | Workforce and L&OD |  |  |
| Sharing Information | Share information regarding the career and training options available across Bridgewater – be the voice of L&OD | EDI |  | Ongoing |
| PPDR | Embed talent management, career progression and equality and inclusion discussions in PPDR | EDI and L&OD |  | March 2021 |
| Supporting staff |  |  |  |  |
| Risk Assessment | Continue to risk assess workplaces and staff re Covid 19 through a quality assured process | Board |  | Ongoing |
| Reasonable Adjustments | - Review Trust arrangements for reasonable adjustment management and provision, and Access to Work - Tailor and ratify reasonable adjustments for staff policy and procedure - Continue roll out of Employee Adjustment Passport | EDI and Board HR HR | Improved NHS Staff Survey scores 50% of known disabled staff to have completed passport | March 2021 March 2021 March 2021 |
| Health and Wellbeing Conversations | Develop using national guidance templates and guides for HWB conversations with staff as part of PPDR | People Hub – supported by EDI |  | October 2020 |
| Staff Networks | - Continue to support the establishment of staff networks for race, disability, LGBT+ - Investigate options for women’s network and network for carers | EDI EDI |  | Ongoing March 2021 |
| Bespoke Support | Continue to provide information on bespoke and tailored support for diverse staff groups via staff networks and internal communications | EDI |  | Ongoing |
| Supporting communities |  |  |  |  |
| Engagement | Develop engagement and consultation strategy for patients and communities | Patient and Public Engagement Group |  | March 2021 |
| EqIA | Develop new template EqIA for considering EDI and human rights across the Trust | EDI – supported by Cheshire & Merseyside EDI Consultant |  | March 2021 |
| Language Interpretation Standard | Ratify Language Interpretation Quality Standard developed across Cheshire and Merseyside | Finance – supported by EDI | Before commencement of procurement of new language interpretation contract | December 2020 |
| House Writing Guide | Review Trust House Writing Guide against accessibility standards and recommendations | Patient Leaflet Group – Supported by EDI |  | March 2021 |
| Rainbow Badges | Continue roll out of NHS Rainbow Badges training and pledges | Staffside – supported by EDI | 75% of staff/services pledged | March 2021 |
| Transgender | Ratify the Cheshire and Merseyside Gender Re-assignment policy and procedure | CCPG and HRPG – supported by EDI |  | March 2021 - TBC |
| Reasonable Adjustments – See Data |  |  |  |  |
| BSL Provider | Relook at proposal for utilising St Helens Deafness Resource Centre for BSL interpretation | Finance and EDI |  | March 2021 |
| LD Standard | Self-assessment and project planning for national, mandatory LD Standard | Quality Matrons – supported by EDI |  | November 2020 |