## Sheet1
WDES Action Plan 2024 - 2026
Trust: | Bridgewater Community Healthcare NHS FT
Year: | 2024
Primary author(s) of this Action Plan | Ruth Besford (EDI Manager)
Plan endorsed by: | Paula Woods (Director of People & OD)
Sources of information underpinning the Plan: | Enabled Network engagement. NHS Staff Survey 2019 - 2023. ESR/employee relations data. NHS Jobs.
| Please specify which actions are different to current practice, and which are continuation | Please specify KPIs and timelines for monitoring the actions | Progress | How will actions be made sustainable
Actions around WDES Metric 1: Recruitment and Promotion | New: Induction/onboarding | Developing guidance for corporate and local induction for disabled and neurodiverse staff and students. By November 2024 |  | Embedded processes with monitoring and review
Actions around WDES Metric 2: Appointments | New: Recruitment | Review options for sharing recruitment activity with wider teams to enable communications with their service users. By September 2024 |  | Embedded activity and communications
Actions around WDES Metric 3: Capability | New: Enhancing equality in people processes | Develop equality in people processes training offer: Unconscious bias Equality, Diversity and Inclusion Legislation By December 2024 |  | Embedded training offers, with monitoring and review
|  | Draft training offer proposal for equality allies in people processes – lived experience, and advocates. By December 2024 |  | Embedded training offers, with monitoring and review
Actions around WDES Metric 4: Bullying, harassment, and abuse | Ongoing: Civility and respect | Use NHS Staff Survey and employee relations data establish a baseline for discrimination, harassment, bullying, abuse and physical violence. By July 2024
|  | Establish regular monitoring and review in EDI Working Group. By September 2024 |  | Working group business cycle
|  | Agree Trust target for reduction of bullying, harassment, discrimination, and violence. By September 2024 |  | Trust governance
|  | Undertake staff network engagement on civility and respect. By October 2024 |  | Monitoring and review
Develop a communications plan for implementation of new civility and respect approach. By November 2024
Implement communications plan. By December 2024
Actions around WDES Metric 5: Equal Opportunities for Career Progression | New: Coaching offers | Develop offer for coaching support for Trust staff network members to support career progression and talent management. By March 2025 |  | Monitoring and review
|  | Develop offer for coaching/coach development training for staff network members. By March 2025 |  | Monitoring and review
Actions around WDES Metric 6: Pressure to attend work whilst unwell | New: Wellbeing and Sickness Absence Policy | Plan and deliver a staff network engagement day,including health and wellbeing, talent management and career conversations, FTSU, and reasonable adjustments/staff support. By October 2024
Actions around WDES Metric 7: Feeling Valued
Actions around WDES Metric 8: Reasonable Adjustments | New: Neurodiversity and disability | Establish task and finish group to develop and implement a plan to embed inclusion support and activities for neurodivergent and disabled staff. By July 2024 |  | Working Group business cycle, Trust governance
Staff engagement on issues, barriers, and successes. By September 2024
Review reasonable adjustments pathways. By October 2024
Review toolkits and templates for Trust usage, e.g. sensory audit tool. By October 2024
Review touchpoints and develop plan for ‘reasonable adjustments and support’ conversations. By October 2024
|  | Develop policy/process/toolkit for reasonable adjustments. By November 2024 |  | Planned review and monitoring
Establish resources/support library/repository. By December 2024
Review wider Trust policy for touch points. By August 2024
Establish points of advice contacts. By September 2024
Review manager training needs. By November 2024
Develop training offer for neurodiversity in the workplace. By December 2024
|  | Implement training offer. By March 2025 |  | Embedded training offers, with monitoring and review
Develop communications and engagement/events plan. By October 2024
Actions around WDES Metric 9: Staff engagement | Ongoing: Staff networks | Commission OD team to review staff network’s structure, form and function. By September 2024 |  | Staff network maturity review through Trust governance
Actions around WDES Metric 10: Board representation
Other components of trust plan | Ongoing: Data - ESR self-reporting | Engage with communications team to develop a comms plan to target self-reporting within the workforce. By August 2024 |  | Monitoring and review of data
Delivery of communications plan. By December 2024
Identification of other contact/touch points with staff to include this message. By September 2024
| Ongoing: Data - Gap analysis | Review all EDI reporting requirements to identify potential gaps in data collection and review, for example in events, leadership training, etc. By September 2024
| New: Inclusive communications and engagement plan | Development of inclusive communications plan, e.g. neurodivergent, sensory impairment, staff on the go etc. By October 2024 |  | Staff network feedback
|  | Implementation of plan. By December 2024 |  | Staff network feedback
Development of annual engagement and awareness events plan. By December 2024
| New: Accessible and inclusive spaces plan. | Develop a plan for access and inclusion in estates. By December 2024 |  | Staff network feedback
|  | Develop a plan for inclusive and accessible workspaces. By December 2024 |  | Staff network feedback
|  | Develop a plan for inclusive and accessible events. By December 2024 |  | Staff network feedback
|  | Develop a guide to free or easily accessible resources. By December 2024 |  | Staff network feedback
| New: Training E.g. Neurodivergence Managing a multi-culture/diverse team Cultural awareness Active bystander Transgender Masterclasses Blended/bite size sessions. International recruits and culture (of the staff or community). Cultural awareness, and pastoral care. | TNA – corporate level. By March 2025
TNA – service engagement. By November 2024
To develop a training offer for People Promise Champions aligned to Compassionate and Inclusive. By December 2024