## Sheet1
WRES Action Plan 2024 - 2026
Trust: | Bridgewater Community Healthcare NHS FT
Year: | 2024
Primary author(s) of this Action Plan | Ruth Besford (EDI Manager)
Plan endorsed by: | Paula Woods (Director of People & OD)
Sources of information underpinning the Plan: | NHS Staff Survey 2015 - 2023. Race Inclusion Network Engagement. NW Black, Asian, and Minority Ethnic Assembly Anti-Racism Framework. ESR. NHS Jobs.
| Please specify which actions are different to current practice, and which are continuation | Please specify KPIs and timelines for monitoring the actions | Progress | How will actions be made sustainable
Actions around WRES Indicator 1: Recruitment and Promotion | New: Induction/onboarding | Developing guidance for corporate and local induction for overseas/international staff and students. By November 2024 |  | Embedded processes with monitoring and review
Actions around WRES Indicator 2: Appointments | New: Recruitment | Review options for sharing recruitment activity with wider teams to enable communications with their service users. By September 2024 |  | Embedded activity and communications
Actions around WRES Indicator 3: Disciplinary | New: Enhancing equality in people processes | Develop equality in people processes training offer: Unconscious bias Equality, Diversity and Inclusion Legislation By December 2024 |  | Embedded training offers, with monitoring and review
|  | Draft training offer proposal for equality allies in people processes – lived experience, and advocates. By December 2024 |  | Embedded training offers, with monitoring and review
Actions around WRES Indicator 4: Education
Actions around WRES Indicator 5 and 6: Bullying, harassment, and abuse | Ongoing: Civility and respect | Use NHS Staff Survey and employee relations data establish a baseline for discrimination, harassment, bullying, abuse and physical violence. By July 2024
|  | Establish regular monitoring and review in EDI Working Group. By September 2024 |  | Working group business cycle
|  | Agree Trust target for reduction of bullying, harassment, discrimination, and violence. By September 2024 |  | Trust governance
|  | Undertake staff network engagement on civility and respect. By October 2024 |  | Monitoring and review
Develop a communications plan for implementation of new civility and respect approach. By November 2024
Implement communications plan. By December 2024
Actions around WRES Indicator 7: Equal Opportunities for Career Progression | New: Coaching offers | Develop offer for coaching support for Trust staff network members to support career progression and talent management. By March 2025 |  | Monitoring and review
|  | Develop offer for coaching/coach development training for staff network members. By March 2025 |  | Monitoring and review
Actions around WRES Indicator 8: Discrimination from a Leader | See WRES Indicators 5 and 6 actions
Actions around WRES Indicator 9: Board representation
Other components of trust plan | Ongoing: Data - ESR self-reporting | Engage with communications team to develop a comms plan to target self-reporting within the workforce. By August 2024 |  | Monitoring and review of data
Delivery of communications plan. By December 2024
Identification of other contact/touch points with staff to include this message. By September 2024
| Ongoing: Data - Gap analysis | Review all EDI reporting requirements to identify potential gaps in data collection and review, for example in events, leadership training, etc. By September 2024
| Ongoing: Staff networks | Commission OD team to review staff network’s structure, form and function. By September 2024 |  | Staff network maturity review through Trust governance
| New: Inclusive communications and engagement plan | Development of inclusive communications plan, e.g. international staff, neurodivergent, sensory impairment, staff on the go etc. By October 2024 |  | Staff network feedback
|  | Implementation of plan. By December 2024 |  | Staff network feedback
Development of annual engagement and awareness events plan. By December 2024
| New: Accessible and inclusive spaces plan. | Develop a plan for access and inclusion in estates. By December 2024 |  | Staff network feedback
|  | Develop a plan for inclusive and accessible workspaces. By December 2024 |  | Staff network feedback
|  | Develop a plan for inclusive and accessible events. By December 2024 |  | Staff network feedback
|  | Develop a guide to free or easily accessible resources. By December 2024 |  | Staff network feedback
| New: Training E.g. Neurodivergence Managing a multi-culture/diverse team Cultural awareness Active bystander Transgender Masterclasses Blended/bite size sessions. International recruits and culture (of the staff or community). Cultural awareness, and pastoral care. | TNA – corporate level. By March 2025
TNA – service engagement. By November 2024
To develop a training offer for People Promise Champions aligned to Compassionate and Inclusive. By December 2024